## Sheet1
PRODUCT BACKLOG FOR ONLINE BANKING APPLICATION
PRODUCT BACKLOG ID | PRIORITY | USER STORY ID | USER STORIES | SCRUM TEAM ASSIGNED | USER STORY STEP DEFINITION 1 | USER STORY STEP DEFINITION 2 | ASSIGNED TO | ESTIMATED TIME | ACTUAL TIME | STATUS | REMARK
1 | high | user001 | Account Management | team1 | Create account | Verify identity | Ravi | 3 days | 3 days | In progress | NA
2 | medium | user002 | Fund Transfers | team2 | Initiate transfer | Confirm transfer | Mansi | 2 days | 2 days | not started | NA
3 | high | user003 | Bill Payments | team3 | Add biller | Pay bill | Rushikesh | 1 day | 1 day | not started | NA
4 | medium | user004 | User Registration | team4 | Fill registration form | Verify email | Priya | 3 days | 4 days | In progress | NA
5 | high | user005 | Loan Management | team5 | Apply for loan | Upload documents | Yashwanth | 5 days | 4 days | not started | NA
6 | medium | user006 | Investment Services | team6 | Select investment | Confirm investment | Raushan | 4 days | 3 days | completed | NA
7 | low | user007 | Notifications | team7 | Set notification preferences | Receive notifications | Neelesh | 2 days | 2 days | not started | NA
8 | medium | user008 | Customer Support | team8 | Submit query | Get response | Shahwaz | 2 days | 2 days | pending | NA
9 | high | user009 | Admin Dashboard | team9 | View analytics | Manage users | Mriganka | 6 days | 6 days | not started | NA

## Sheet2
SPRINT BACKLOG FOR ONLINE BANKING APPLICATION
User Story ID | User Story name |  | User Story Definition |  | Assigned To | Estimated Time | Status | Remarks
|  | As a <type of user> | I want to <perform some task> | So that <Ican achieve some goals>
user 004 | User Registration |  |  |  | Priya | 3 days
task1 | Login ID | As an end user | I want to set Login ID | So that I can Login into application |  | 10 hrs | completed | NA
task2 | Set Password | As an end user | I want to set Password | So that I can resgister into Application |  | 12 hrs | in progress | NA
task3 | Reset password | As an end user | I want to Reset my password | So that I can change my password |  | 15 hrs | pending | NA
task4 | User Database | As an admin | I want to create user database | So that I can manage user data |  | 21 hrs | in progress | NA
task5 | User Interface | As an admin | I want to create user friendly interface | So that user can login easily |  | 5 hrs | in progress | NA
task6 | Password Reset | As an admin | I want to allow user to reset password | So that user can update password |  | 7 hrs | pending | NA
task7 | captcha integration | As an admin | I want to integrate captcha | So that user can be verified |  | 4 hrs | completed | NA
user 001 | Account Management |  |  |  | Ravi | 3 days
task1 | Create Account | As an end user | I want to enter personal details | So that I can update personal information |  | 10 hrs | completed | NA
task2 | View Transaction History | As an end user | I want to view transaction details | So that I can keep track on my transactions |  | 12 hrs | in progress | NA
task3 | View Account Summary | As an end user | I want to view Account Summary | So that I can quickly see my balance |  | 11 hrs | completed | NA
task4 | Manage Accounts | As an admin | I want to create database of all users | So that I can assist them with issues |  | 19 hrs | completed | NA
task5 | Audit Account logs | As an admin | I want to audit logs of account activites | So that I can ensure security compliances |  | 12 hrs | in progress | NA
user 009 | Admin Dashboard |  |  |  | Mriganka | 6 days
task1 | View Summary | As an admin | I want to view summary of dashboard | So that I can monitor overall application |  | 24 hrs | completed | NA
task2 | Audit Account Logs | As an admin | I want to audit logs of admin actions | So that I can ensure security compliances |  | 20 hrs | pending | NA
task3 | Generate System Report | As an admin | I want to generate system report | So that I can analyze performace |  | 15 hrs | in progress | NA
task4 | Control Access | As an admin | I want to manage roles and permission | So that I can control access of some parts of application |  | 12 hrs | in progress | NA

## Sheet3
Defect Report of Online Banking Application
Defect ID | Defect | Created on | Creator | Assigned To | Severity | Priority | Status
D001 | Unable to Login | 2024-03-06 | Ravi | Rushi | high | high | open
D002 | unable to see Transaction details | 2024-03-05 | Mansi | Ravi | high | medium | close
D003 | Unable to access Account Details | 2024-05-06 | Rushi | Priya | high | high | open
D004 | Unable to update Account details | 2024-02-03 | mansi | Priya | medium | low | open
D005 | Trasaction summary not found | 2024-01-06 | Ravi | Mriganka | medium | low | close
D006 | Admin Portal is not available | 2024-04-05 | Shahvaz | Yashvanth | high | high | close
D007 | Password Reset Option is not there | 2024-06-06 | Yashwanth | Mriganka | low | medium | close
D008 | Unable to get notifications | 2024-06-06 | Mansi | Ravi | low | low | open
D009 | Unable to access Loan details | 2024-03-03 | Priya | Ravi | medium | medium | open